## info
Projekt MedCycleTour
Mediteranska ruta – EuroVelo 8
Plan aktivnosti razvoja rute za Hrvatsku
za razdoblje od 2018 do 2030. g.
Dodatak: tablični prikaz svih aktivnosti koje su prikazane u dokumentu
Project MedCycleTour
Mediterranean route – EuroVelo 8
Action plan for the development of the Croatian route
for the period from 2018 to 2030
Appendix: overview of all actions presented in the document

## hrvatski
Poglavlje | Br. | kriterij ECS | Rok | vrsta aktivnosti | pojedinosti | Info 2 | dionica | km dionice | dužina (km) | županija | procjena troška (€) | ECF klasifikacija
5.1.1 | 1 | dodatni | 2020 | uklanjanje zapreke | 3 km iza Umaga - zapreka na biciklističkoj stazi, obilazak po travi moguć |  | 97 | 28 |  | IŽ | 100 | 1.3.4
5.1.1 | 2 | dodatni | 2020 | uklanjanje zapreke | Barbariga - ulaz na stazu uz more |  | 98 | 55 |  | IŽ | 100 | 1.3.4
5.1.1 | 3 | dodatni | 2020 | uklanjanje zapreke | Nin - guranje bicikla preko mosta |  | 107 | 39 |  | ZŽ | 100 | 1.3.4
5.1.1 | 4 | dodatni | 2020 | uklanjanje zapreke | Zadar - guranje bicikla preko mosta |  | 107 | 60 |  | ZŽ | 100 | 1.3.4
5.1.1 | 5 | dodatni | 2020 | uklanjanje zapreke | Izlaz s magistrale nakon Prosike |  | 109 | 13 |  | ŠKŽ | 100 | 1.3.4
5.1.1 | 6 | dodatni | 2020 | uklanjanje zapreke | Povratak na magistralu nakon Prosike |  | 109 | 15 |  | ŠKŽ | 100 | 1.3.4
5.1.1 | 7 | važan | 2020 | uklanjanje zapreke | prag od 40 cm na ogradi između dva turistička naselja |  | 110 | 51 |  | SDŽ | 50 | 1.3.4
5.1.1 | 8 | važan | 2020 | uklanjanje zapreke | izlaz iz Dubrovnika na cestu kod Orsule |  | 116 | 6 |  | DNŽ | 100 | 1.3.4
5.1.2 | 1 | važan | 2020 | smirenje prometa | Zambratija | D75 | 1 |  | 2 km | IŽ | 600 | 1.3.2
5.1.2 | 2 | važan | 2020 | smirenje prometa | Karigador | D75 | 1 |  | 3 km | IŽ | 300 | 1.3.2
5.1.2 | 3 | važan | 2020 | smirenje prometa | Antenal | D75 | 1 |  | 3 km | IŽ | 300 | 1.3.2
5.1.2 | 4 | važan | 2020 | smirenje prometa | Funtana | D75 | 1 |  | 0,4 km | IŽ | 300 | 1.3.2
5.1.2 | 5 | važan | 2020 | smirenje prometa | Limski kanal | D75 | 2 |  | 6 km | IŽ | 300 | 1.3.2
5.1.2 | 6 | važan | 2020 | smirenje prometa | Fažana-Valbandon | Lokalna | 2 |  | 4 km | IŽ | 600 | 1.3.2
5.1.2 | 7 | važan | 2020 | smirenje prometa | Pula | Pula | 2 |  | 6 km | IŽ | 600 | 1.3.2
5.1.2 | 8 | važan | 2020 | smirenje prometa | Barban-Raša | D66 | 3 |  | 6 km | IŽ | 600 | 1.3.2
5.1.2 | 9 | bitan | 2020 | smirenje prometa | Kršan-Vozilići | D64/D500 | 4 |  | 2 km | IŽ | 600 | 1.3.2
5.1.2 | 10 | važan | 2020 | smirenje prometa | Medveja-Rijeka | D66 | 4 |  | 20 km | PGŽ | 900 | 1.3.2
5.1.2 | 11 | važan | 2020 | smirenje prometa | Rijeka |  | 4 |  | 4 km | PGŽ | 600 | 1.3.2
5.1.2 | 12 | bitan | 2020 | smirenje prometa | Rijeka – Bakar – Križišće | D8 | 5 |  | 12 km | PGŽ | 1800 | 1.3.2
5.1.2 | 13 | važan | 2020 | smirenje prometa | Maslenica | D8 | 11 |  | 1,5 km | ZŽ | 300 | 1.3.2
5.1.2 | 14 | bitan | 2020 | smirenje prometa | Prosika | D8 | 13 |  | 2,7 km | ŠKŽ | 600 | 1.3.2
5.1.2 | 15 | bitan | 2020 | smirenje prometa | Pirovac 1 | D8 | 13 |  | 1,7 km | ŠKŽ | 600 | 1.3.2
5.1.2 | 16 | bitan | 2020 | smirenje prometa | Pirovac 2 | D8 | 13 |  | 1,8 km | ŠKŽ | 600 | 1.3.2
5.1.2 | 17 | bitan | 2020 | smirenje prometa | Most – Šibenik | D8 | 13 |  | 1,7 km | ŠKŽ | 600 | 1.3.2
5.1.2 | 18 | bitan | 2020 | smirenje prometa | Brodarica Grebaštica | D8 | 14 |  | 5,3 km | ŠKŽ | 900 | 1.3.2
5.1.2 | 19 | važan | 2020 | smirenje prometa | Seget Vranjica | D8 | 14 |  | 300 m | SDŽ | 600 | 1.3.2
5.1.2 | 20 | važan | 2020 | smirenje prometa | Trogir ulaz | Trogir | 14 |  | 1 km | SDŽ | 300 | 1.3.2
5.1.2 | 21 | važan | 2020 | smirenje prometa | Trogir - izlaz | Trogir | 15 |  | 2,5 km | SDŽ | 300 | 1.3.2
5.1.2 | 22 | važan | 2020 | smirenje prometa | Kaštel Gomilica Sućurac | Franje Tuđmana | 15 |  | 2 km | SDŽ | 300 | 1.3.2
5.1.2 | 23 | važan | 2020 | smirenje prometa | Solin | Frane Bulića | 15 |  | 1,3 km | SDŽ | 300 | 1.3.2
5.1.2 | 24 | važan | 2020 | smirenje prometa | ulaz u Split | Splitska | 15 |  | 600 m | SDŽ | 300 | 1.3.2
5.1.2 | 25 | važan | 2020 | smirenje prometa | Brela | D8 | 16 |  | 4 km | SDŽ | 300 | 1.3.2
5.1.2 | 26 | važan | 2020 | smirenje prometa | Podgora | D8 | 17 |  | 2,3 km | SDŽ | 300 | 1.3.2
5.1.2 | 27 | važan | 2020 | smirenje prometa | Živogošće Drvenik | D8 | 17 |  | 8 km | SDŽ | 1200 | 1.3.2
5.1.2 | 28 | važan | 2020 | smirenje prometa | Gradac Ploče | D8 | 17 |  | 11 km | DNŽ | 900 | 1.3.2
5.1.2 | 29 | važan | 2020 | smirenje prometa | Dubrava Ston | D414 | 18 |  | 20 km | DNŽ | 2400 | 1.3.2
5.1.2 | 30 | bitan | 2020 | smirenje prometa | Zaton – Dubrovnik most | D8 | 19 |  | 8 km | DNŽ | 1500 | 1.3.2
5.1.2 | 31 | bitan | 2020 | smirenje prometa | Dubac | D8 | 20 |  | 1 km | DNŽ | 600 | 1.3.2
5.1.2 | 32 | bitan | 2020 | smirenje prometa | Kupari Zvekovica | D8 | 20 |  | 8 km | DNŽ | 1200 | 1.3.2
5.1.3 | 4-1 | bitan | 2025 | priprema izgradnje | Zambratija | D75 | 1 |  | 2 | IŽ | 15000 | 1.1.1
5.1.3 | 4-13 | važan | 2025 | priprema izgradnje | Maslenica | D8 | 11 |  | 1 | ZŽ | 10500 | 1.1.1
5.1.3 | 4-14 | bitan | 2025 | priprema izgradnje | Prosika | D8 | 13 |  | 2.7 | ŠKŽ | 28000 | 1.1.1
5.1.3 | 4-15 | bitan | 2025 | priprema izgradnje | Pirovac 1 | D8 | 13 |  | 1.7 | ŠKŽ | 18750 | 1.1.1
5.1.3 | 4-17 | bitan | 2020 | priprema izgradnje | Most – Šibenik | D8 | 13 |  | 1.7 | ŠKŽ | 12750 | 1.1.1
5.1.3 | 4-18 | bitan | 2025 | priprema izgradnje | Brodarica - Grebaštica | D8 | 14 |  | 5.3 | ŠKŽ | 74000 | 1.1.1
5.1.3 | 4-19 | važan | 2025 | priprema izgradnje | Seget Vranjica | D8 | 14 |  | 0.3 | SDŽ | 2250 | 1.1.1
5.1.3 | 4-2 | važan | 2025 | priprema izgradnje | Karigador | D75 | 1 |  | 3 | IŽ | 22500 | 1.1.1
5.1.3 | 4-20 | važan | 2025 | priprema izgradnje | Trogir ulaz | Trogir | 14 |  | 1 | SDŽ | 7500 | 1.1.1
5.1.3 | 4-23 | važan | 2025 | priprema izgradnje | Solin | Frane Bulića | 15 |  | 1.3 | SDŽ | 13650 | 1.1.1
5.1.3 | 4-24 | važan | 2025 | priprema izgradnje | ulaz u Split | Splitska | 15 |  | 0.6 | SDŽ | 6450 | 1.1.1
5.1.3 | 4-25 | važan | 2025 | priprema izgradnje | Brela | D8 | 16 |  | 4 | SDŽ | 80000 | 1.1.1
5.1.3 | 4-26 | važan | 2030 | priprema izgradnje | Podgora | D8 | 17 |  | 2.3 | SDŽ | 46000 | 1.1.1
5.1.3 | 4-27 | važan | 2030 | priprema izgradnje | Živogošće - Drvenik | D8 | 17 |  | 8 | SDŽ | 160000 | 1.1.1
5.1.3 | 4-28 | važan | 2030 | priprema izgradnje | Gradac - Ploče | D8 | 17 |  | 11 | DNŽ | 220000 | 1.1.1
5.1.3 | 4-3 | važan | 2030 | priprema izgradnje | Antenal | D75 | 1 |  | 3 | IŽ | 54000 | 1.1.1
5.1.3 | 4-30 | bitan | 2030 | priprema izgradnje | Zaton – Dubrovnik most | D8 | 19 |  | 8 | DNŽ | 180000 | 1.1.1
5.1.3 | 4-31 | bitan | 2025 | priprema izgradnje | Dubac | D8 | 20 |  | 1 | DNŽ | 25000 | 1.1.1
5.1.3 | 4-32 | bitan | 2025 | priprema izgradnje | Kupari - Zvekovica | D8 | 20 |  | 8 | DNŽ | 146000 | 1.1.1
5.1.3 | 4-33 | važan | 2025 | priprema izgradnje | stube Brela |  | 16 |  | 0.3 | SDŽ | 6000 | 1.1.1
5.1.3 | 4-34 | važan | 2025 | priprema izgradnje | stube Tučepi |  | 17 |  | 0.1 | SDŽ | 2400 | 1.1.1
5.1.3 | 4-35 | važan | 2025 | priprema izgradnje | stube Podgora |  | 17 |  | 0.3 | SDŽ | 6000 | 1.1.1
5.1.3 | 4-36 | važan | 2025 | priprema izgradnje | proširenje mosta u Brodarici |  | 14 |  | 0.01 | ŠKŽ | 2000 | 1.1.1
5.1.3 | 4-37 | važan | 2025 | priprema izgradnje | raskrižje u Grebaštici |  | 14 |  | 0.01 | ŠKŽ | 5000 | 1.1.1
5.1.3 | 4-38 | važan | 2025 | priprema izgradnje | raskrižje u Zatonu Dubrovačkom |  | 19 |  | 0.02 | DNŽ | 8000 | 1.1.1
5.1.3 | 4-39 | važan | 2030 | priprema izgradnje | raskrižje Maslenica |  | 11 |  | 0.02 | ZŽ | 8000 | 1.1.1
5.1.3 | 4-8 | važan | 2030 | priprema izgradnje | Barban-Raša | D66 | 3 |  | 6 | IŽ | 90000 | 1.1.1
5.1.3 | 4-9 | bitan | 2025 | priprema izgradnje | Kršan-Vozilići | D64/D500 | 4 |  | 2 | IŽ | 15000 | 1.1.1
5.1.3 | 5-1 | važan | 2020 | priprema uređenja | Pomer - Medulin |  |  |  | 0.5 | IŽ | 1500 | 1.1.1
5.1.3 | 5-10 | važan | 2020 | priprema uređenja | blizu Kavrana |  |  |  | 2 | IŽ | 2400 | 1.1.1
5.1.3 | 5-11 | važan | 2025 | priprema uređenja | kratke dionice prije Šibenskog mosta |  |  |  | 1.5 | ŠKŽ | 4500 | 1.1.1
5.1.3 | 5-12 | važan | 2020 | priprema uređenja | Između Sapina Doca i Gustirne |  |  |  | 1 | ŠKŽ | 1200 | 1.1.1
5.1.3 | 5-13 | važan | 2025 | priprema uređenja | između TN Medena i TN Belvedere |  |  |  | 1 | SDŽ | 1200 | 1.1.1
5.1.3 | 5-14 | važan | 2020 | priprema uređenja | dio oko Splitske zračne luke |  |  |  | 1 | SDŽ | 1200 | 1.1.1
5.1.3 | 5-15 | važan | 2025 | priprema uređenja | dio između Makarske i Tučepa |  |  |  | 2 | SDŽ | 1200 | 1.1.1
5.1.3 | 5-16 | važan | 2020 | priprema uređenja | prije Igrana |  |  |  | 3 | SDŽ | 1200 | 1.1.1
5.1.3 | 5-17 | važan | 2025 | priprema uređenja | prije Drvenika |  |  |  | 1 | SDŽ | 1200 | 1.1.1
5.1.3 | 5-18 | važan | 2020 | priprema uređenja | Konjevac - Orašac |  |  |  | 1 | DNŽ | 1200 | 1.1.1
5.1.3 | 5-19 | važan | 2025 | priprema uređenja | Tušići - D8 |  |  |  | 2 | DNŽ | 1200 | 1.1.1
5.1.3 | 5-2 | bitan | 2020 | priprema uređenja | Vratnik |  |  |  | 1.7 | LSŽ | 17000 | 1.1.1
5.1.3 | 5-20 | bitan | 2025 | priprema uređenja | Pirovac - Ivinj |  |  |  | 2 | ŠKŽ | 6000 | 1.1.1
5.1.3 | 5-3 | važan | 2020 | priprema uređenja | Stolac - Oltari |  |  |  | 6 | LSŽ | 2400 | 1.1.1
5.1.3 | 5-4 | važan | 2020 | priprema uređenja | Uz Vransko jezero, dionice između Drage i Prosike |  |  |  | 2 | ŠKŽ | 6000 | 1.1.1
5.1.3 | 5-5 | važan | 2020 | priprema uređenja | odvojak od D8 prema Šibeniku |  |  |  | 0.4 | ŠKŽ | 1200 | 1.1.1
5.1.3 | 5-7 | važan | 2020 | priprema uređenja | Konjevac - Orašac |  |  |  | 0.5 | DNŽ | 1500 | 1.1.1
5.1.3 | 5-8 | važan | 2025 | priprema uređenja | Gospić - Ostrvica |  |  |  | 3 | LSŽ | 3600 | 1.1.1
5.1.3 | 5-9 | važan | 2020 | priprema uređenja | blizu Medulina |  |  |  | 1 | IŽ | 3000 | 1.1.1
5.1.4 | 1 | bitan | 2025 | izgradnja | Zambratija | D75 | 1 |  | 2 | IŽ | 398500 | 1.1.2
5.1.4 | 2 | važan | 2025 | izgradnja | Karigador | D75 | 1 |  | 3 | IŽ | 372000 | 1.1.2
5.1.4 | 3 | važan | 2030 | izgradnja | Antenal | D75 | 1 |  | 3 | IŽ | 960000 | 1.1.2
5.1.4 | 8 | važan | 2030 | izgradnja | Barban-Raša | D66 | 3 |  | 6 | IŽ | 1080000 | 1.1.2
5.1.4 | 9 | bitan | 2025 | izgradnja | Kršan-Vozilići | D64/D500 | 4 |  | 2 | IŽ | 248000 | 1.1.2
5.1.4 | 13 | važan | 2025 | izgradnja | Maslenica | D8 | 11 |  | 1 | ZŽ | 126000 | 1.1.2
5.1.4 | 14 | bitan | 2025 | izgradnja | Prosika | D8 | 13 |  | 2.7 | ŠKŽ | 393200 | 1.1.2
5.1.4 | 15 | bitan | 2025 | izgradnja | Pirovac 1 | D8 | 13 |  | 1.7 | ŠKŽ | 376000 | 1.1.2
5.1.4 | 17 | bitan | 2020 | izgradnja | Most – Šibenik | D8 | 13 |  | 1.7 | ŠKŽ | 210800 | 1.1.2
5.1.4 | 18 | bitan | 2025 | izgradnja | Brodarica - Grebaštica | D8 | 14 |  | 5.3 | ŠKŽ | 930000 | 1.1.2
5.1.4 | 19 | važan | 2025 | izgradnja | Seget Vranjica | D8 | 14 |  | 0.3 | SDŽ | 127500 | 1.1.2
5.1.4 | 20 | važan | 2025 | izgradnja | Trogir ulaz | Trogir | 14 |  | 1 | SDŽ | 425000 | 1.1.2
5.1.4 | 23 | važan | 2025 | izgradnja | Solin | Frane Bulića | 15 |  | 1.3 | SDŽ | 597500 | 1.1.2
5.1.4 | 24 | važan | 2025 | izgradnja | ulaz u Split | Splitska | 15 |  | 0.6 | SDŽ | 277500 | 1.1.2
5.1.4 | 25 | važan | 2025 | izgradnja | Brela | D8 | 16 |  | 4 | SDŽ | 880000 | 1.1.2
5.1.4 | 26 | važan | 2030 | izgradnja | Podgora | D8 | 17 |  | 2.3 | SDŽ | 506000 | 1.1.2
5.1.4 | 27 | važan | 2030 | izgradnja | Živogošće - Drvenik | D8 | 17 |  | 8 | SDŽ | 1760000 | 1.1.2
5.1.4 | 28 | važan | 2030 | izgradnja | Gradac - Ploče | D8 | 17 |  | 11 | DNŽ | 2420000 | 1.1.2
5.1.4 | 30 | bitan | 2030 | izgradnja | Zaton – Dubrovnik most | D8 | 19 |  | 8 | DNŽ | 2000000 | 1.1.2
5.1.4 | 31 | bitan | 2025 | izgradnja | Dubac | D8 | 20 |  | 1 | DNŽ | 280000 | 1.1.2
5.1.4 | 32 | bitan | 2025 | izgradnja | Kupari - Zvekovica | D8 | 20 |  | 8 | DNŽ | 3000000 | 1.1.2
5.1.4 | 33 | važan | 2025 | izgradnja | stube Brela |  | 16 |  | 0.3 | SDŽ | 66000 | 1.1.2
5.1.4 | 34 | važan | 2025 | izgradnja | stube Tučepi |  | 17 |  | 0.1 | SDŽ | 26400 | 1.1.2
5.1.4 | 35 | važan | 2025 | izgradnja | stube Podgora |  | 17 |  | 0.3 | SDŽ | 66000 | 1.1.2
5.1.4 | 36 | važan | 2025 | izgradnja | proširenje mosta u Brodarici |  | 14 |  | 0.01 | ŠKŽ | 20000 | 1.1.4
5.1.4 | 37 | važan | 2025 | izgradnja | raskrižje u Grebaštici |  | 14 |  | 0.01 | ŠKŽ | 50000 | 1.1.5
5.1.4 | 38 | važan | 2025 | izgradnja | raskrižje u Zatonu Dubrovačkom |  | 19 |  | 0.02 | DNŽ | 80000 | 1.1.5
5.1.4 | 39 | važan | 2030 | izgradnja | raskrižje Maslenica |  | 11 |  | 0.02 | ZŽ | 80000 | 1.1.5
5.1.5 | 1 | važan | 2020 | uređenje makadama | Pomer - Medulin |  |  |  | 0.5 | IŽ | 15000 | 1.1.3
5.1.5 | 2 | bitan | 2020 | uređenje makadama | Vratnik |  |  |  | 1.7 | LSŽ | 170000 | 1.1.3
5.1.5 | 3 | važan | 2020 | uređenje makadama | Stolac - Oltari |  |  |  | 6 | LSŽ | 24000 | 1.1.3
5.1.5 | 4 | važan | 2020 | uređenje makadama | Uz Vransko jezero, dionice između Drage i Prosike |  |  |  | 2 | ŠKŽ | 60000 | 1.1.3
5.1.5 | 5 | važan | 2020 | uređenje makadama | odvojak od D8 prema Šibeniku |  |  |  | 0.4 | ŠKŽ | 12000 | 1.1.3
5.1.5 | 7 | važan | 2020 | uređenje makadama | Konjevac - Orašac |  |  |  | 0.5 | DNŽ | 15000 | 1.1.3
5.1.5 | 8 | važan | 2025 | uređenje makadama | Gospić - Ostrvica |  |  |  | 3 | LSŽ | 36000 | 1.1.3
5.1.5 | 9 | važan | 2020 | uređenje makadama | blizu Medulina |  |  |  | 1 | IŽ | 30000 | 1.1.3
5.1.5 | 10 | važan | 2020 | uređenje makadama | blizu Kavrana |  |  |  | 2 | IŽ | 24000 | 1.1.3
5.1.5 | 11 | važan | 2025 | uređenje makadama | kratke dionice prije Šibenskog mosta |  |  |  | 1.5 | ŠKŽ | 45000 | 1.1.3
5.1.5 | 12 | važan | 2020 | uređenje makadama | Između Sapina Doca i Gustirne |  |  |  | 1 | ŠKŽ | 12000 | 1.1.3
5.1.5 | 13 | važan | 2025 | uređenje makadama | između TN Medena i TN Belvedere |  |  |  | 1 | SDŽ | 12000 | 1.1.3
5.1.5 | 14 | važan | 2020 | uređenje makadama | dio oko Splitske zračne luke |  |  |  | 1 | SDŽ | 12000 | 1.1.3
5.1.5 | 15 | važan | 2025 | uređenje makadama | dio između Makarske i Tučepa |  |  |  | 2 | SDŽ | 12000 | 1.1.3
5.1.5 | 16 | važan | 2020 | uređenje makadama | prije Igrana |  |  |  | 3 | SDŽ | 12000 | 1.1.3
5.1.5 | 17 | važan | 2025 | uređenje makadama | prije Drvenika |  |  |  | 1 | SDŽ | 12000 | 1.1.3
5.1.5 | 18 | važan | 2020 | uređenje makadama | Konjevac - Orašac |  |  |  | 1 | DNŽ | 12000 | 1.1.3
5.1.5 | 19 | važan | 2025 | uređenje makadama | Tušići - D8 |  |  |  | 2 | DNŽ | 12000 | 1.1.3
5.1.5 | 20 | bitan | 2025 | uređenje makadama | Pirovac - Ivinj |  |  |  | 2 | ŠKŽ | 60000 | 1.1.3
5.1.6 | 1 | bitan | 2020 | putokazi | EV8-97 (HR 1) Slovenija - Vrsar |  | 1 |  | 76 | IŽ | 22000 | 1.3.5
5.1.6 | 2 | bitan | 2020 | putokazi | EV8-98 (HR 2) Vrsar - Pula |  | 2 |  | 73 | IŽ | 12000 | 1.3.5
5.1.6 | 3 | bitan | 2020 | putokazi | EV8-101 (HR 5) Rijeka - Bater |  | 5 |  | 57 | PGŽ | 6500 | 1.3.5
5.1.6 | 4 | bitan | 2020 | putokazi | EV8-102 (HR 6) Bater - Krasno |  | 6 |  | 14 | PGŽ | 1000 | 1.3.5
5.1.6 | 5 | bitan | 2020 | putokazi | EV8-102 (HR 6) Bater - Krasno |  | 6 |  | 38 | LSŽ | 3500 | 1.3.5
5.1.6 | 6 | bitan | 2020 | putokazi | EV8-103 (HR 7) Krasno - izvor Gacke |  | 7 |  | 41 | LSŽ | 4500 | 1.3.5
5.1.6 | 7 | bitan | 2020 | putokazi | EV8-104 (HR 8) izvor Gacke - Gospić |  | 8 |  | 47 | LSŽ | 5000 | 1.3.5
5.1.6 | 8 | bitan | 2020 | putokazi | EV8-105 (HR 9) Gospić - Lovinac |  | 9 |  | 42 | LSŽ | 4500 | 1.3.5
5.1.6 | 9 | bitan | 2020 | putokazi | EV8-107 (HR 11) Maslenica - Zadar |  | 11 |  | 60 | ZŽ | 7000 | 1.3.5
5.1.6 | 10 | bitan | 2020 | putokazi | EV8-108 (HR 12) Zadar - Pakoštane |  | 12 |  | 43 | ZŽ | 10000 | 1.3.5
5.1.6 | 11 | bitan | 2020 | putokazi | EV8-109 (HR 13) Pakoštane - Šibenik |  | 13 |  | 6 | ZŽ | 1000 | 1.3.5
5.1.6 | 12 | bitan | 2020 | putokazi | EV8-109 (HR 13) Pakoštane - Šibenik |  | 13 |  | 42 | ŠKŽ | 9000 | 1.3.5
5.1.6 | 13 | bitan | 2020 | putokazi | EV8-110 (HR 14) Šibenik - Trogir |  | 14 |  | 41 | ŠKŽ | 6500 | 1.3.5
5.1.6 | 14 | bitan | 2020 | putokazi | EV8-110 (HR 14) Šibenik - Trogir |  | 14 |  | 15 | SDŽ | 3000 | 1.3.5
5.1.6 | 15 | bitan | 2020 | putokazi | EV8-111 (HR 15) Trogir - Split |  | 15 |  | 39 | SDŽ | 9500 | 1.3.5
5.1.6 | 16 | bitan | 2020 | putokazi | EV8-112 (HR 16) Split - Makarska |  | 16 |  | 75 | SDŽ | 11000 | 1.3.5
5.1.6 | 17 | bitan | 2020 | putokazi | EV8-113 (HR 17) Makarska - Trpanj |  | 17 |  | 45 | SDŽ | 8500 | 1.3.5
5.1.6 | 18 | bitan | 2020 | putokazi | EV8-113 (HR 17) Makarska - Trpanj |  | 17 |  | 12 | DNŽ | 2000 | 1.3.5
5.1.6 | 19 | bitan | 2020 | putokazi | EV8-114 (HR 18) Trpanj - Ston |  | 18 |  | 54 | DNŽ | 7000 | 1.3.5
5.1.6 | 20 | bitan | 2020 | putokazi | EV8-115 (HR 19) Ston - Dubrovnik |  | 19 |  | 56 | DNŽ | 7000 | 1.3.5
5.1.7.1 | 1 | bitan | 2020 | lokalni javni prijevoz | (Mošćenička Draga) Opatija-Rijeka | Brod |  |  |  | PGŽ | 2000 | 1.4.2
5.1.7.1 | 2 | bitan | 2020 | lokalni javni prijevoz | Dubrovnik – Cavtat | Brod |  |  |  | DNŽ | 2000 | 1.4.2
5.1.7.1 | 3 | bitan | 2020 | lokalni javni prijevoz | Mošćenička Draga (Opatija) – Rijeka | Autobus |  |  |  | PGŽ | 2000 | 1.4.2
5.1.7.1 | 4 | bitan | 2020 | lokalni javni prijevoz | Dubrovnik – Zvekovica (Cavtat) | Autobus |  |  |  | DNŽ | 2000 | 1.4.2
5.1.7.1 | 5 | važan | 2020 | lokalni javni prijevoz | Limski Kanal - Rovinj | Brod |  |  |  | IŽ | 2000 | 1.4.2
5.1.7.1 | 6 | važan | 2020 | lokalni javni prijevoz | Rab – Lun | Brod |  |  |  | PGŽ | 1000 | 1.4.2
5.1.7.1 | 7 | važan | 2020 | lokalni javni prijevoz | Rijeka – Križišće | Autobus |  |  |  | PGŽ | 2000 | 1.4.2
5.1.7.1 | 8 | važan | 2020 | lokalni javni prijevoz | Vodice - Šibenik | Autobus |  |  |  | ŠKŽ | 2000 | 1.4.2
5.1.7.1 | 9 | važan | 2020 | lokalni javni prijevoz | Šibenik – Grebaštica | Autobus |  |  |  | ŠKŽ | 2000 | 1.4.2
5.1.7.1 | 10 | važan | 2020 | lokalni javni prijevoz | Trogir – Kaštel Štafilić (Kaštel Stari) | Autobus |  |  |  | SDŽ | 2000 | 1.4.2
5.1.7.1 | 11 | važan | 2020 | lokalni javni prijevoz | Zaton – Dubrovnik | Autobus |  |  |  | DNŽ | 2000 | 1.4.2
5.1.7.2 | 1 | Bitan | 2020 | dostupnost javnim prijevozom | Ljubljana – Pula, uvođenje mogućnosti za prijevoz bicikala | Vlak |  |  |  |  | 5000 | 1.4.2
5.1.7.2 | 2 | Bitan | 2020 | dostupnost javnim prijevozom | Rijeka – Pula | Autobus |  |  |  |  | 4000 | 1.4.2
5.1.7.2 | 3 | Bitan | 2020 | dostupnost javnim prijevozom | Zagreb – Zadar – Šibenik – Split – Makarska – Ploče – Dubrovnik (kombinacija dvije linije) | Autobus |  |  |  |  | 8000 | 1.4.2
5.1.7.2 | 4 | Važan | 2020 | dostupnost javnim prijevozom | Rijeka – Zadar preko Like Rijeka – Zadar duž obale | Autobus |  |  |  |  | 4000 | 1.4.2
5.1.7.2 | 5 | Bitan | 2020 | dostupnost javnim prijevozom | Katamaranska linija Pula – Mali Lošinj da prevozi bicikle – određen kapacitet i mogućnost rezervacije | Brod |  |  |  |  | 3000 | 1.4.2
5.1.7.2 | 6 | Važan | 2025 | dostupnost javnim prijevozom | Dostupnost prijevoza bicikala dva puta dnevno po zapadnoj obali Istre od Umaga do Pule | Autobus |  |  |  |  | 4000 | 1.4.2
5.1.7.2 | 7 | Važan | 2025 | dostupnost javnim prijevozom | Dostupnost prijevoza bicikala dva puta dnevno iz Maslenice, Nina, Biograda, Rogoznice, Primoštena, Trogira, Omiša, Brela, Makarske, Drvenika, Stona, Slanog, Trstena, Cavtata | Autobus |  |  |  |  | 8000 | 1.4.2
5.1.8 | 1 |  | 2025 | brojači bic. prometa | Uvođenje 2 brojača biciklističkog prometa |  |  |  |  | IŽ | 3000 | 1.7.1
5.1.8 | 2 |  | 2025 | brojači bic. prometa | Uvođenje 2 brojača biciklističkog prometa |  |  |  |  | PGŽ | 3000 | 1.7.1
5.1.8 | 3 |  | 2025 | brojači bic. prometa | Uvođenje 2 brojača biciklističkog prometa |  |  |  |  | LSŽ | 3000 | 1.7.1
5.1.8 | 4 |  | 2025 | brojači bic. prometa | Uvođenje 2 brojača biciklističkog prometa |  |  |  |  | ZŽ | 3000 | 1.7.1
5.1.8 | 5 |  | 2025 | brojači bic. prometa | Uvođenje 2 brojača biciklističkog prometa |  |  |  |  | ŠKŽ | 3000 | 1.7.1
5.1.8 | 6 |  | 2025 | brojači bic. prometa | Uvođenje 2 brojača biciklističkog prometa |  |  |  |  | SDŽ | 3000 | 1.7.1
5.1.8 | 7 |  | 2025 | brojači bic. prometa | Uvođenje 2 brojača biciklističkog prometa |  |  |  |  | DNŽ | 3000 | 1.7.1
5.2.1 | 1 |  | 2020 | najam bicikala i opreme | Subvencija uvođenja mreže za najam bicikala - razvoj 4 stanice | [5 empty] | 40000 | 2.3.3
5.2.1 | 2 |  | 2025 | najam bicikala i opreme | Subvencija uspostave sustava e-bicikala (npr. 40% cijene za 250 e-bicikala prosječne cijene 1.500 eura) | [5 empty] | 150000 | 2.3.3
5.2.1 | 3 |  | 2025 | najam bicikala i opreme | Subvencija uvođenja mreže za najam bicikala - razvoj 10 stanica | [5 empty] | 100000 | 2.3.3
5.2.2 | 1 | Bitan | 2020 | servis za bicikle | servisna stanica na dionici EV8-101 (HR 5) Rijeka - Bater | Bribir |  |  |  | PGŽ | 600 | 2.3.1
5.2.2 | 2 | Bitan | 2020 | servis za bicikle | servisna stanica na dionici EV8-105 (HR 9) Gospić - Lovinac | Lovinac |  |  |  | LSŽ | 600 | 2.3.1
5.2.2 | 3 | Bitan | 2020 | servis za bicikle | servisna stanica na dionici EV8-106 (HR 10) Lovinac - Maslenica | Maslenica |  |  |  | ZŽ | 600 | 2.3.1
5.2.2 | 4 | Bitan | 2020 | servis za bicikle | servisna stanica na dionici EV8-110 (HR 14) Šibenik - Trogir | Trogir |  |  |  | ŠKŽ | 600 | 2.3.1
5.2.2 | 5 | Bitan | 2020 | servis za bicikle | servisna stanica na dionici EV8-113 (HR 17) Makarska - Trpanj | Trpanj |  |  |  | DNŽ | 600 | 2.3.1
5.2.2 | 6 | Bitan | 2020 | servis za bicikle | servisna stanica na dionici EV8-114 (HR 18) Trpanj - Ston | Ston |  |  |  | DNŽ | 600 | 2.3.1
5.2.2 | 7 | Bitan | 2020 | servis za bicikle | servisna stanica na dionici EV8-116 (HR 20) Dubrovnik - granica | Cavtat |  |  |  | DNŽ | 600 | 2.3.1
5.2.2 | 8 | Važan | 2020 | servis za bicikle | subvencija marketinga servisa za bicikle | [5 empty] | 3000 | 2.3.1
5.2.2 | 9 | Važan | 2025 | servis za bicikle | Uvođenje 10 novih servisera za bicikle | [5 empty] | 15000 | 2.3.1
5.2.3 | 1 | važan | 2025 | razvoj taksija za bicikle | Subvencija nosača i zaštite od kiše za 4 bicikla za 2 broda za liniju Novigrad (Istra) – Červar Porat | brod |  |  |  | IŽ | 1500 | 1.4.2
5.2.3 | 2 | važan | 2025 | razvoj taksija za bicikle | Subvencija nosača i zaštite od kiše za 4 bicikla za 2 broda za liniju Limski Kanal - Rovinj | brod |  |  |  | IŽ | 1500 | 1.4.2
5.2.3 | 3 | bitan | 2020 | razvoj taksija za bicikle | Subvencija nosača i zaštite od kiše za 4 bicikla za 2 broda za liniju Opatija - Rijeka | brod |  |  |  | PGŽ | 1500 | 1.4.2
5.2.3 | 4 | dodatni | 2030 | razvoj taksija za bicikle | Subvencija nosača i zaštite od kiše za 4 bicikla za 2 broda za liniju Povljana – Vir | brod |  |  |  | ZŽ | 1500 | 1.4.2
5.2.3 | 5 | važan | 2025 | razvoj taksija za bicikle | Subvencija nosača i zaštite od kiše za 4 bicikla za 2 broda za liniju Srima – Šibenik | brod |  |  |  | ŠKŽ | 1500 | 1.4.2
5.2.3 | 6 | važan | 2025 | razvoj taksija za bicikle | Subvencija nosača i zaštite od kiše za 4 bicikla za 2 broda za liniju Trogir – Kaštel Štafilić | brod |  |  |  | SDŽ | 1500 | 1.4.2
5.2.3 | 7 | važan | 2025 | razvoj taksija za bicikle | Subvencija nosača i zaštite od kiše za 4 bicikla za 2 broda za liniju Kaštel Sućurac - Split | brod |  |  |  | SDŽ | 1500 | 1.4.2
5.2.3 | 8 | dodatni | 2030 | razvoj taksija za bicikle | Subvencija nosača i zaštite od kiše za 4 bicikla za 2 broda za liniju Gradac - Ploče | brod |  |  |  | SDŽ/DNŽ | 1500 | 1.4.2
5.2.3 | 9 | važan | 2025 | razvoj taksija za bicikle | Subvencija nosača i zaštite od kiše za 4 bicikla za 2 broda za liniju Zaton - Dubrovnik | brod |  |  |  | DNŽ | 1500 | 1.4.2
5.2.3 | 10 | bitan | 2020 | razvoj taksija za bicikle | Subvencija nosača i zaštite od kiše za 4 bicikla za 2 broda za liniju Dubrovnik - Cavtat | brod |  |  |  | DNŽ | 1500 | 1.4.2
5.2.3 | 11 | dodatni | 2025 | razvoj taksija za bicikle | Subvencija po 4 krovna nosača za bicikle za 4 taksi prijevoznika | auto |  |  |  | IŽ | 3000 | 1.4.2
5.2.3 | 12 | dodatni | 2025 | razvoj taksija za bicikle | Subvencija po 4 krovna nosača za bicikle za 4 taksi prijevoznika | auto |  |  |  | PGŽ | 3000 | 1.4.2
5.2.3 | 13 | dodatni | 2025 | razvoj taksija za bicikle | Subvencija po 4 krovna nosača za bicikle za 4 taksi prijevoznika | auto |  |  |  | LSŽ | 3000 | 1.4.2
5.2.3 | 14 | dodatni | 2025 | razvoj taksija za bicikle | Subvencija po 4 krovna nosača za bicikle za 4 taksi prijevoznika | auto |  |  |  | ZŽ | 3000 | 1.4.2
5.2.3 | 15 | dodatni | 2025 | razvoj taksija za bicikle | Subvencija po 4 krovna nosača za bicikle za 4 taksi prijevoznika | auto |  |  |  | ŠKŽ | 3000 | 1.4.2
5.2.3 | 16 | dodatni | 2025 | razvoj taksija za bicikle | Subvencija po 4 krovna nosača za bicikle za 4 taksi prijevoznika | auto |  |  |  | SDŽ | 3000 | 1.4.2
5.2.3 | 17 | dodatni | 2025 | razvoj taksija za bicikle | Subvencija po 4 krovna nosača za bicikle za 4 taksi prijevoznika | auto |  |  |  | DNŽ | 3000 | 1.4.2
5.2.6 | 1 | bitan | 2020 | razvoj smještaja | subvencija razvoja jednostavnog "bike-friendly" smještajnog kapaciteta u jednoj kući za 5-6 gostiju |  |  |  |  | PGŽ | 15000 | 2.1.1
5.2.6 | 2 | važan | 2020 | razvoj smještaja | subvencija razvoja jednostavnog "bike-friendly" kampa za 10 šatora |  |  |  |  | PGŽ | 10000 | 2.1.1
5.2.6 | 3 | bitan | 2020 | razvoj smještaja | subvencija razvoja jednostavnog "bike-friendly" smještajnog kapaciteta u dvije kuće za po 5-6 gostiju |  |  |  |  | LSŽ | 30000 | 2.1.1
5.2.6 | 4 | dodatni | 2025 | razvoj smještaja | razvoj jednostavnog smještajnog i ugostiteljskog kapaciteta u Mogoriću za 20 biciklista |  |  |  |  | LSŽ | 40000 | 2.1.1
5.2.7 | 1 | dodatni | 2025 | odmorište | Izgradnja biciklističkog odmorišta između Križišća i Bribira |  |  |  |  | PGŽ | 8000 | 2.1.3
5.2.7 | 2 | dodatni | 2025 | odmorište | Izgradnja biciklističkog odmorišta između Krivog puta i Oltara |  |  |  |  | LSŽ | 8000 | 2.1.3
5.2.7 | 3 | dodatni | 2025 | odmorište | Izgradnja biciklističkog odmorišta između Vrila Gacke i Perušića |  |  |  |  | LSŽ | 8000 | 2.1.3
5.2.7 | 4 | dodatni | 2025 | odmorište | Izgradnja biciklističkog odmorišta između Gospića i Mogorića |  |  |  |  | LSŽ | 8000 | 2.1.3
5.2.7 | 5 | dodatni | 2025 | odmorište | Izgradnja biciklističkog odmorišta u Mogoriću |  |  |  |  | LSŽ | 8000 | 2.1.3
5.2.7 | 6 | dodatni | 2025 | odmorište | Izgradnja biciklističkog odmorišta između Žuljane i Stona |  |  |  |  | DNŽ | 8000 | 2.1.3
5.2.8 | 1 |  | 2025 | čuvanje bicikla s prtljagom | za ukupno 20 bicikala na 2-3 mjesta u županiji |  |  |  |  | IŽ | 15000 | 2.3.2
5.2.8 | 2 |  | 2025 | čuvanje bicikla s prtljagom | za ukupno 20 bicikala na 2-3 mjesta u županiji |  |  |  |  | PGŽ | 15000 | 2.3.2
5.2.8 | 3 |  | 2025 | čuvanje bicikla s prtljagom | za ukupno 20 bicikala na 2-3 mjesta u županiji |  |  |  |  | LSŽ | 15000 | 2.3.2
5.2.8 | 4 |  | 2025 | čuvanje bicikla s prtljagom | za ukupno 20 bicikala na 2-3 mjesta u županiji |  |  |  |  | ZŽ | 15000 | 2.3.2
5.2.8 | 5 |  | 2025 | čuvanje bicikla s prtljagom | za ukupno 20 bicikala na 2-3 mjesta u županiji |  |  |  |  | ŠKŽ | 15000 | 2.3.2
5.2.8 | 6 |  | 2025 | čuvanje bicikla s prtljagom | za ukupno 20 bicikala na 2-3 mjesta u županiji |  |  |  |  | SDŽ | 15000 | 2.3.2
5.2.8 | 7 |  | 2025 | čuvanje bicikla s prtljagom | za ukupno 20 bicikala na 2-3 mjesta u županiji |  |  |  |  | DNŽ | 15000 | 2.3.2
5.3.1 | 1 | bitan | 2020 | Internet | Ažuriranje internetskih stranica rute novim informacijama u 2019 i 2020. g. | [5 empty] | 10000 | 3.3.2
5.3.1 | 2 | važan | 2020 | Internet | Nastavak razvoja internetskih stranica (napredne mogućnosti, društvene mreže, newsletter, aplikacije) | [5 empty] | 8000 | 3.3.2
5.3.1 | 3 |  | 2020 | info centar | pilot usluge "Hot line" za EuroVelo 8 u Hrvatskoj 2020.g | [5 empty] | 3000
5.3.1 | 4 | bitan | 2025 | Internet | Održvanje web stranice 2021-2022. g. | [5 empty] | 5000 | 3.3.2
5.3.1 | 5 | bitan | 2025 | info sistem | Uspostava modela financijski samoodrživog ažuriranja detaljnih informacija o ruti od 2021. g. | [5 empty] | 5000
5.3.3 | 1 | bitan | 2020 | tiskani materijali | Organizacija tiskanja karte i vodiča za rutu EuroVelo 8 u Hrvatskoj | [5 empty] | 5000 | 3.3.3.
5.3.4 | 1 |  | 2020 | promocija | Ukupno razne promotivne aktivnosti u 2019. i 2020. g. | [5 empty] | 40000 | 3.3
5.3.4 | 2 |  | 2025 | promocija | Ukupno razne promotivne aktivnosti 2021-2025. g. | [5 empty] | 100000 | 3.3
5.3.5 | 1 |  | 2020 | marketing | plan marketinga do 2022. | [5 empty] | 10000 | 3.1.1
5.3.5 | 2 |  | 2025 | marketing | plan marketinga do 2030. | [5 empty] | 10000 | 3.1.1
5.3.5 | 3 |  | 2020 | marketing | Organizacija sustavnog praćenja podacima o cikloturistima (npr. integracijom u sustav e-visitor) | [5 empty] | 5000 | 3.1.2
5.3.5 | 4 |  | 2025 | marketing | Detaljna istraživanja o korišetnju rute (brojači, feedback preko web stranica, anketiranje, obrada rezultata) | [5 empty] | 25000 | 3.1.2
5.4.1 | 1 |  | 2025 | organizacija | trošak organizacije (ljudi, putevi, radionice i sl.) 2021-2025.g. | [5 empty] | 150000 | 4.3.3
5.4.1 | 2 |  | 2030 | organizacija | trošak organizacije (ljudi, putevi, radionice i sl.) 2026-2030.g. | [5 empty] | 100000 | 4.3.3
5.4.2 | 1 |  | 2020 | istraživanje rute | Istraživanje i optimiranje rute do 2020. g. | [5 empty] | 5000 | 4.2.1
5.4.2 | 2 |  | 2025 | istraživanje rute | Istraživanje i optimiranje rute do 2021-2025. g. | [5 empty] | 15000 | 4.2.1
5.4.2 | 3 |  | 2030 | istraživanje rute | Istraživanje i optimiranje rute do 2026-2030. g. | [5 empty] | 5000 | 4.2.1
5.4.4 | 1 |  | 2025 | certificiranje | certificiranje dijela rute | [5 empty] | 10000 | 4.4.2
5.4.4 | 2 |  | 2030 | certificiranje | certificiranje kompletne rute | [5 empty] | 10000 | 4.4.2
5.4.5 | 1 |  | 2020 | radionice | radionice i konferencije u 2020. g. | [5 empty] | 5000 | 4.1.1
5.4.5 | 2 |  | 2025 | radionice | radionice i konferencije 2021-2025.g. | [5 empty] | 20000 | 4.1.1
5.4.6 | 1 |  | 2020 | treninzi | treninzi i studijska putovanja do 2020. g. | [5 empty] | 18000 | 4.1.2
5.4.6 | 2 |  | 2025 | treninzi | treninzi i studijska putovanja do 2025. g. | [5 empty] | 18000 | 4.1.2

## English
Chapter | Nr. | ECS Level | Term | Action | Detail | Detail 2 | Section | km in the section | length (km) | County | Costs estimation (€) | ECF classification
5.1.1 | 1 | additional | 2020 | barrier removal | 3 km after Umag, avoidance possible |  | 97 | 28 |  | IŽ | 100 | 1.3.4
5.1.1 | 2 | additional | 2020 | barrier removal | Barbariga - entrance to the path along the beach |  | 98 | 55 |  | IŽ | 100 | 1.3.4
5.1.1 | 3 | additional | 2020 | barrier removal | Nin - bike pushing over the bridge |  | 107 | 39 |  | ZŽ | 100 | 1.3.4
5.1.1 | 4 | additional | 2020 | barrier removal | Zadar - bike pushing over the bridge |  | 107 | 60 |  | ZŽ | 100 | 1.3.4
5.1.1 | 5 | additional | 2020 | barrier removal | exit from D8 road after Prosika |  | 109 | 13 |  | ŠKŽ | 100 | 1.3.4
5.1.1 | 6 | additional | 2020 | barrier removal | return to D8 road after Prosika |  | 109 | 15 |  | ŠKŽ | 100 | 1.3.4
5.1.1 | 7 | important | 2020 | barrier removal | barrier 40 cm between two touristic villages |  | 110 | 51 |  | SDŽ | 50 | 1.3.4
5.1.1 | 8 | important | 2020 | barrier removal | exit from Dubrovnik to D8 road close to Orsula park |  | 116 | 6 |  | DNŽ | 100 | 1.3.4
5.1.2 | 1 | important | 2020 | traffic calming | Zambratija | D75 | 97 |  | 2 km | IŽ | 600 | 1.3.2
5.1.2 | 2 | important | 2020 | traffic calming | Karigador | D75 | 97 |  | 3 km | IŽ | 300 | 1.3.2
5.1.2 | 3 | important | 2020 | traffic calming | Antenal | D75 | 97 |  | 3 km | IŽ | 300 | 1.3.2
5.1.2 | 4 | important | 2020 | traffic calming | Funtana | D75 | 97 |  | 0,4 km | IŽ | 300 | 1.3.2
5.1.2 | 5 | important | 2020 | traffic calming | Limski kanal | D75 | 98 |  | 6 km | IŽ | 300 | 1.3.2
5.1.2 | 6 | important | 2020 | traffic calming | Fažana-Valbandon | Local | 98 |  | 4 km | IŽ | 600 | 1.3.2
5.1.2 | 7 | important | 2020 | traffic calming | Pula | Pula | 98 |  | 6 km | IŽ | 600 | 1.3.2
5.1.2 | 8 | important | 2020 | traffic calming | Barban-Raša | D66 | 99 |  | 6 km | IŽ | 600 | 1.3.2
5.1.2 | 9 | essential | 2020 | traffic calming | Kršan-Vozilići | D64/D500 | 100 |  | 2 km | IŽ | 600 | 1.3.2
5.1.2 | 10 | important | 2020 | traffic calming | Medveja-Rijeka | D66 | 100 |  | 20 km | PGŽ | 900 | 1.3.2
5.1.2 | 11 | important | 2020 | traffic calming | Rijeka |  | 100 |  | 4 km | PGŽ | 600 | 1.3.2
5.1.2 | 12 | essential | 2020 | traffic calming | Rijeka – Bakar – Križišće | D8 | 101 |  | 12 km | PGŽ | 1800 | 1.3.2
5.1.2 | 13 | important | 2020 | traffic calming | Maslenica | D8 | 107 |  | 1,5 km | ZŽ | 300 | 1.3.2
5.1.2 | 14 | essential | 2020 | traffic calming | Prosika | D8 | 109 |  | 2,7 km | ŠKŽ | 600 | 1.3.2
5.1.2 | 15 | essential | 2020 | traffic calming | Pirovac 1 | D8 | 109 |  | 1,7 km | ŠKŽ | 600 | 1.3.2
5.1.2 | 16 | essential | 2020 | traffic calming | Pirovac 2 | D8 | 109 |  | 1,8 km | ŠKŽ | 600 | 1.3.2
5.1.2 | 17 | essential | 2020 | traffic calming | Bridge – Šibenik | D8 | 109 |  | 1,7 km | ŠKŽ | 600 | 1.3.2
5.1.2 | 18 | essential | 2020 | traffic calming | Brodarica Grebaštica | D8 | 110 |  | 5,3 km | ŠKŽ | 900 | 1.3.2
5.1.2 | 19 | important | 2020 | traffic calming | Seget Vranjica | D8 | 110 |  | 300 m | SDŽ | 600 | 1.3.2
5.1.2 | 20 | important | 2020 | traffic calming | Trogir entrance | Trogir | 110 |  | 1 km | SDŽ | 300 | 1.3.2
5.1.2 | 21 | important | 2020 | traffic calming | Trogir exit | Trogir | 111 |  | 2,5 km | SDŽ | 300 | 1.3.2
5.1.2 | 22 | important | 2020 | traffic calming | Kaštel Gomilica Sućurac | Franje Tuđmana | 111 |  | 2 km | SDŽ | 300 | 1.3.2
5.1.2 | 23 | important | 2020 | traffic calming | Solin | Frane Bulića | 111 |  | 1,3 km | SDŽ | 300 | 1.3.2
5.1.2 | 24 | important | 2020 | traffic calming | Split entrance | Splitska | 111 |  | 600 m | SDŽ | 300 | 1.3.2
5.1.2 | 25 | important | 2020 | traffic calming | Brela | D8 | 112 |  | 4 km | SDŽ | 300 | 1.3.2
5.1.2 | 26 | important | 2020 | traffic calming | Podgora | D8 | 113 |  | 2,3 km | SDŽ | 300 | 1.3.2
5.1.2 | 27 | important | 2020 | traffic calming | Živogošće Drvenik | D8 | 113 |  | 8 km | SDŽ | 1200 | 1.3.2
5.1.2 | 28 | important | 2020 | traffic calming | Gradac Ploče | D8 | 113 |  | 11 km | DNŽ | 900 | 1.3.2
5.1.2 | 29 | important | 2020 | traffic calming | Dubrava Ston | D414 | 114 |  | 20 km | DNŽ | 2400 | 1.3.2
5.1.2 | 30 | essential | 2020 | traffic calming | Zaton – Dubrovnik bridge | D8 | 115 |  | 8 km | DNŽ | 1500 | 1.3.2
5.1.2 | 31 | essential | 2020 | traffic calming | Dubac | D8 | 116 |  | 1 km | DNŽ | 600 | 1.3.2
5.1.2 | 32 | essential | 2020 | traffic calming | Kupari Zvekovica | D8 | 116 |  | 8 km | DNŽ | 1200 | 1.3.2
5.1.3 | 4-1 | essential | 2025 | construction preparation | Zambratija | D75 | 97 |  | 2 | IŽ | 15000 | 1.1.1
5.1.3 | 4-13 | important | 2025 | construction preparation | Maslenica | D8 | 107 |  | 1 | ZŽ | 10500 | 1.1.1
5.1.3 | 4-14 | essential | 2025 | construction preparation | Prosika | D8 | 109 |  | 2.7 | ŠKŽ | 28000 | 1.1.1
5.1.3 | 4-15 | essential | 2025 | construction preparation | Pirovac 1 | D8 | 109 |  | 1.7 | ŠKŽ | 18750 | 1.1.1
5.1.3 | 4-17 | essential | 2020 | construction preparation | Most – Šibenik | D8 | 109 |  | 1.7 | ŠKŽ | 12750 | 1.1.1
5.1.3 | 4-18 | essential | 2025 | construction preparation | Brodarica - Grebaštica | D8 | 110 |  | 5.3 | ŠKŽ | 74000 | 1.1.1
5.1.3 | 4-19 | important | 2025 | construction preparation | Seget Vranjica | D8 | 110 |  | 0.3 | SDŽ | 2250 | 1.1.1
5.1.3 | 4-2 | important | 2025 | construction preparation | Karigador | D75 | 97 |  | 3 | IŽ | 22500 | 1.1.1
5.1.3 | 4-20 | important | 2025 | construction preparation | Trogir ulaz | Trogir | 110 |  | 1 | SDŽ | 7500 | 1.1.1
5.1.3 | 4-23 | important | 2025 | construction preparation | Solin | Frane Bulića | 111 |  | 1.3 | SDŽ | 13650 | 1.1.1
5.1.3 | 4-24 | important | 2025 | construction preparation | entrance to Split | Splitska | 111 |  | 0.6 | SDŽ | 6450 | 1.1.1
5.1.3 | 4-25 | important | 2025 | construction preparation | Brela | D8 | 112 |  | 4 | SDŽ | 80000 | 1.1.1
5.1.3 | 4-26 | important | 2030 | construction preparation | Podgora | D8 | 113 |  | 2.3 | SDŽ | 46000 | 1.1.1
5.1.3 | 4-27 | important | 2030 | construction preparation | Živogošće - Drvenik | D8 | 113 |  | 8 | SDŽ | 160000 | 1.1.1
5.1.3 | 4-28 | important | 2030 | construction preparation | Gradac - Ploče | D8 | 113 |  | 11 | DNŽ | 220000 | 1.1.1
5.1.3 | 4-3 | important | 2030 | construction preparation | Antenal | D75 | 97 |  | 3 | IŽ | 54000 | 1.1.1
5.1.3 | 4-30 | essential | 2030 | construction preparation | Zaton – Dubrovnik bridge | D8 | 115 |  | 8 | DNŽ | 180000 | 1.1.1
5.1.3 | 4-31 | essential | 2025 | construction preparation | Dubac | D8 | 116 |  | 1 | DNŽ | 25000 | 1.1.1
5.1.3 | 4-32 | essential | 2025 | construction preparation | Kupari - Zvekovica | D8 | 116 |  | 8 | DNŽ | 146000 | 1.1.1
5.1.3 | 4-33 | important | 2025 | construction preparation | stairways Brela |  | 112 |  | 0.3 | SDŽ | 6000 | 1.1.1
5.1.3 | 4-34 | important | 2025 | construction preparation | stairways Tučepi |  | 113 |  | 0.1 | SDŽ | 2400 | 1.1.1
5.1.3 | 4-35 | important | 2025 | construction preparation | stairways Podgora |  | 113 |  | 0.3 | SDŽ | 6000 | 1.1.1
5.1.3 | 4-36 | important | 2025 | construction preparation | bridge widening in Brodarica |  | 110 |  | 0.01 | ŠKŽ | 2000 | 1.1.1
5.1.3 | 4-37 | important | 2025 | construction preparation | crossing in Grebaštica |  | 110 |  | 0.01 | ŠKŽ | 5000 | 1.1.1
5.1.3 | 4-38 | important | 2025 | construction preparation | crossing in Zaton (Dubrovnik) |  | 115 |  | 0.02 | DNŽ | 8000 | 1.1.1
5.1.3 | 4-39 | important | 2030 | construction preparation | crossing Maslenica |  | 107 |  | 0.02 | ZŽ | 8000 | 1.1.1
5.1.3 | 4-8 | important | 2030 | construction preparation | Barban-Raša | D66 | 99 |  | 6 | IŽ | 90000 | 1.1.1
5.1.3 | 4-9 | essential | 2025 | construction preparation | Kršan-Vozilići | D64/D500 | 100 |  | 2 | IŽ | 15000 | 1.1.1
5.1.3 | 5-1 | important | 2020 | reconstrucion preparation | Between Pomer and Medulin |  |  |  | 0.5 | IŽ | 1500 | 1.1.1
5.1.3 | 5-10 | important | 2020 | reconstrucion preparation | close to Kavran |  |  |  | 2 | IŽ | 2400 | 1.1.1
5.1.3 | 5-11 | important | 2025 | reconstrucion preparation | Short sections before Šibenik bridge |  |  |  | 1.5 | ŠKŽ | 4500 | 1.1.1
5.1.3 | 5-12 | important | 2020 | reconstrucion preparation | between Sapina Doca and Gustirna |  |  |  | 1 | ŠKŽ | 1200 | 1.1.1
5.1.3 | 5-13 | important | 2025 | reconstrucion preparation | section between TN Medena and TN Belvedere |  |  |  | 1 | SDŽ | 1200 | 1.1.1
5.1.3 | 5-14 | important | 2020 | reconstrucion preparation | section close to the Split airport |  |  |  | 1 | SDŽ | 1200 | 1.1.1
5.1.3 | 5-15 | important | 2025 | reconstrucion preparation | between Makarska and Tučepi |  |  |  | 2 | SDŽ | 1200 | 1.1.1
5.1.3 | 5-16 | important | 2020 | reconstrucion preparation | before Igrane |  |  |  | 3 | SDŽ | 1200 | 1.1.1
5.1.3 | 5-17 | important | 2025 | reconstrucion preparation | before Drvenik |  |  |  | 1 | SDŽ | 1200 | 1.1.1
5.1.3 | 5-18 | important | 2020 | reconstrucion preparation | Between Konjevac and Orašac |  |  |  | 1 | DNŽ | 1200 | 1.1.1
5.1.3 | 5-19 | important | 2025 | reconstrucion preparation | between Tušići and D8 |  |  |  | 2 | DNŽ | 1200 | 1.1.1
5.1.3 | 5-2 | essential | 2020 | reconstrucion preparation | Vratnik |  |  |  | 1.7 | LSŽ | 17000 | 1.1.1
5.1.3 | 5-20 | essential | 2025 | reconstrucion preparation | Pirovac - Ivinj |  |  |  | 2 | ŠKŽ | 6000 | 1.1.1
5.1.3 | 5-3 | important | 2020 | reconstrucion preparation | Between Stolac and Oltari |  |  |  | 6 | LSŽ | 2400 | 1.1.1
5.1.3 | 5-4 | important | 2020 | reconstrucion preparation | Short sections along Vransko jezero between Drage and Prosika |  |  |  | 2 | ŠKŽ | 6000 | 1.1.1
5.1.3 | 5-5 | important | 2020 | reconstrucion preparation | Branch from D8 to Šibenik |  |  |  | 0.4 | ŠKŽ | 1200 | 1.1.1
5.1.3 | 5-7 | important | 2020 | reconstrucion preparation | Between Konjevac and Orašac |  |  |  | 0.5 | DNŽ | 1500 | 1.1.1
5.1.3 | 5-8 | important | 2025 | reconstrucion preparation | Gospić - Ostrvica |  |  |  | 3 | LSŽ | 3600 | 1.1.1
5.1.3 | 5-9 | important | 2020 | reconstrucion preparation | Section close to Medulin |  |  |  | 1 | IŽ | 3000 | 1.1.1
5.1.4 | 1 | essential | 2025 | construction | Zambratija | D75 | 97 |  | 2 | IŽ | 398500 | 1.1.2
5.1.4 | 2 | important | 2025 | construction | Karigador | D75 | 97 |  | 3 | IŽ | 372000 | 1.1.2
5.1.4 | 3 | important | 2030 | construction | Antenal | D75 | 97 |  | 3 | IŽ | 960000 | 1.1.2
5.1.4 | 8 | important | 2030 | construction | Barban-Raša | D66 | 99 |  | 6 | IŽ | 1080000 | 1.1.2
5.1.4 | 9 | essential | 2025 | construction | Kršan-Vozilići | D64/D500 | 100 |  | 2 | IŽ | 248000 | 1.1.2
5.1.4 | 13 | important | 2025 | construction | Maslenica | D8 | 107 |  | 1 | ZŽ | 126000 | 1.1.2
5.1.4 | 14 | essential | 2025 | construction | Prosika | D8 | 109 |  | 2.7 | ŠKŽ | 393200 | 1.1.2
5.1.4 | 15 | essential | 2025 | construction | Pirovac 1 | D8 | 109 |  | 1.7 | ŠKŽ | 376000 | 1.1.2
5.1.4 | 17 | essential | 2020 | construction | Most – Šibenik | D8 | 109 |  | 1.7 | ŠKŽ | 210800 | 1.1.2
5.1.4 | 18 | essential | 2025 | construction | Brodarica - Grebaštica | D8 | 110 |  | 5.3 | ŠKŽ | 930000 | 1.1.2
5.1.4 | 19 | important | 2025 | construction | Seget Vranjica | D8 | 110 |  | 0.3 | SDŽ | 127500 | 1.1.2
5.1.4 | 20 | important | 2025 | construction | Trogir ulaz | Trogir | 110 |  | 1 | SDŽ | 425000 | 1.1.2
5.1.4 | 23 | important | 2025 | construction | Solin | Frane Bulića | 111 |  | 1.3 | SDŽ | 597500 | 1.1.2
5.1.4 | 24 | important | 2025 | construction | entrance to Split | Splitska | 111 |  | 0.6 | SDŽ | 277500 | 1.1.2
5.1.4 | 25 | important | 2025 | construction | Brela | D8 | 112 |  | 4 | SDŽ | 880000 | 1.1.2
5.1.4 | 26 | important | 2030 | construction | Podgora | D8 | 113 |  | 2.3 | SDŽ | 506000 | 1.1.2
5.1.4 | 27 | important | 2030 | construction | Živogošće - Drvenik | D8 | 113 |  | 8 | SDŽ | 1760000 | 1.1.2
5.1.4 | 28 | important | 2030 | construction | Gradac - Ploče | D8 | 113 |  | 11 | DNŽ | 2420000 | 1.1.2
5.1.4 | 30 | essential | 2030 | construction | Zaton – Dubrovnik bridge | D8 | 115 |  | 8 | DNŽ | 2000000 | 1.1.2
5.1.4 | 31 | essential | 2025 | construction | Dubac | D8 | 116 |  | 1 | DNŽ | 280000 | 1.1.2
5.1.4 | 32 | essential | 2025 | construction | Kupari - Zvekovica | D8 | 116 |  | 8 | DNŽ | 3000000 | 1.1.2
5.1.4 | 33 | important | 2025 | construction | stairways Brela |  | 112 |  | 0.3 | SDŽ | 66000 | 1.1.2
5.1.4 | 34 | important | 2025 | construction | stairways Tučepi |  | 113 |  | 0.1 | SDŽ | 26400 | 1.1.2
5.1.4 | 35 | important | 2025 | construction | stairways Podgora |  | 113 |  | 0.3 | SDŽ | 66000 | 1.1.2
5.1.4 | 36 | important | 2025 | construction | bridge widening in Brodarica |  | 110 |  | 0.01 | ŠKŽ | 20000 | 1.1.4
5.1.4 | 37 | important | 2025 | construction | crossing in Grebaštica |  | 110 |  | 0.01 | ŠKŽ | 50000 | 1.1.5
5.1.4 | 38 | important | 2025 | construction | crossing in Zaton (Dubrovnik) |  | 115 |  | 0.02 | DNŽ | 80000 | 1.1.5
5.1.4 | 39 | important | 2030 | construction | crossing Maslenica |  | 107 |  | 0.02 | ZŽ | 80000 | 1.1.5
5.1.5 | 1 | important | 2020 | road reconstruction | Between Pomer and Medulin |  |  |  | 0.5 | IŽ | 15000 | 1.1.3
5.1.5 | 2 | essential | 2020 | road reconstruction | Vratnik |  |  |  | 1.7 | LSŽ | 170000 | 1.1.3
5.1.5 | 3 | important | 2020 | road reconstruction | Between Stolac and Oltari |  |  |  | 6 | LSŽ | 24000 | 1.1.3
5.1.5 | 4 | important | 2020 | road reconstruction | Short sections along Vransko jezero between Drage and Prosika |  |  |  | 2 | ŠKŽ | 60000 | 1.1.3
5.1.5 | 5 | important | 2020 | road reconstruction | Branch from D8 to Šibenik |  |  |  | 0.4 | ŠKŽ | 12000 | 1.1.3
5.1.5 | 7 | important | 2020 | road reconstruction | Between Konjevac and Orašac |  |  |  | 0.5 | DNŽ | 15000 | 1.1.3
5.1.5 | 8 | important | 2025 | road reconstruction | Gospić - Ostrvica |  |  |  | 3 | LSŽ | 36000 | 1.1.3
5.1.5 | 9 | important | 2020 | road reconstruction | Section close to Medulin |  |  |  | 1 | IŽ | 30000 | 1.1.3
5.1.5 | 10 | important | 2020 | road reconstruction | close to Kavran |  |  |  | 2 | IŽ | 24000 | 1.1.3
5.1.5 | 11 | important | 2025 | road reconstruction | Short sections before Šibenik bridge |  |  |  | 1.5 | ŠKŽ | 45000 | 1.1.3
5.1.5 | 12 | important | 2020 | road reconstruction | between Sapina Doca and Gustirna |  |  |  | 1 | ŠKŽ | 12000 | 1.1.3
5.1.5 | 13 | important | 2025 | road reconstruction | section between TN Medena and TN Belvedere |  |  |  | 1 | SDŽ | 12000 | 1.1.3
5.1.5 | 14 | important | 2020 | road reconstruction | section close to the Split airport |  |  |  | 1 | SDŽ | 12000 | 1.1.3
5.1.5 | 15 | important | 2025 | road reconstruction | between Makarska and Tučepi |  |  |  | 2 | SDŽ | 12000 | 1.1.3
5.1.5 | 16 | important | 2020 | road reconstruction | before Igrane |  |  |  | 3 | SDŽ | 12000 | 1.1.3
5.1.5 | 17 | important | 2025 | road reconstruction | before Drvenik |  |  |  | 1 | SDŽ | 12000 | 1.1.3
5.1.5 | 18 | important | 2020 | road reconstruction | Between Konjevac and Orašac |  |  |  | 1 | DNŽ | 12000 | 1.1.3
5.1.5 | 19 | important | 2025 | road reconstruction | between Tušići and D8 |  |  |  | 2 | DNŽ | 12000 | 1.1.3
5.1.5 | 20 | essential | 2025 | road reconstruction | Pirovac - Ivinj |  |  |  | 2 | ŠKŽ | 60000 | 1.1.3
5.1.6 | 1 | essential | 2020 | signposting | EV8-97 (HR 1) Slovenija - Vrsar |  | 97 |  | 76 | IŽ | 22000 | 1.3.5
5.1.6 | 2 | essential | 2020 | signposting | EV8-98 (HR 2) Vrsar - Pula |  | 98 |  | 73 | IŽ | 12000 | 1.3.5
5.1.6 | 3 | essential | 2020 | signposting | EV8-101 (HR 5) Rijeka - Bater |  | 101 |  | 57 | PGŽ | 6500 | 1.3.5
5.1.6 | 4 | essential | 2020 | signposting | EV8-102 (HR 6) Bater - Krasno |  | 102 |  | 14 | PGŽ | 1000 | 1.3.5
5.1.6 | 5 | essential | 2020 | signposting | EV8-102 (HR 6) Bater - Krasno |  | 102 |  | 38 | LSŽ | 3500 | 1.3.5
5.1.6 | 6 | essential | 2020 | signposting | EV8-103 (HR 7) Krasno - Gacka river source |  | 103 |  | 41 | LSŽ | 4500 | 1.3.5
5.1.6 | 7 | essential | 2020 | signposting | EV8-104 (HR 8) Gacka river source - Gospić |  | 104 |  | 47 | LSŽ | 5000 | 1.3.5
5.1.6 | 8 | essential | 2020 | signposting | EV8-105 (HR 9) Gospić - Lovinac |  | 105 |  | 42 | LSŽ | 4500 | 1.3.5
5.1.6 | 9 | essential | 2020 | signposting | EV8-107 (HR 11) Maslenica - Zadar |  | 107 |  | 60 | ZŽ | 7000 | 1.3.5
5.1.6 | 10 | essential | 2020 | signposting | EV8-108 (HR 12) Zadar - Pakoštane |  | 108 |  | 43 | ZŽ | 10000 | 1.3.5
5.1.6 | 11 | essential | 2020 | signposting | EV8-109 (HR 13) Pakoštane - Šibenik |  | 109 |  | 6 | ZŽ | 1000 | 1.3.5
5.1.6 | 12 | essential | 2020 | signposting | EV8-109 (HR 13) Pakoštane - Šibenik |  | 109 |  | 42 | ŠKŽ | 9000 | 1.3.5
5.1.6 | 13 | essential | 2020 | signposting | EV8-110 (HR 14) Šibenik - Trogir |  | 110 |  | 41 | ŠKŽ | 6500 | 1.3.5
5.1.6 | 14 | essential | 2020 | signposting | EV8-110 (HR 14) Šibenik - Trogir |  | 110 |  | 15 | SDŽ | 3000 | 1.3.5
5.1.6 | 15 | essential | 2020 | signposting | EV8-111 (HR 15) Trogir - Split |  | 111 |  | 39 | SDŽ | 9500 | 1.3.5
5.1.6 | 16 | essential | 2020 | signposting | EV8-112 (HR 16) Split - Makarska |  | 112 |  | 75 | SDŽ | 11000 | 1.3.5
5.1.6 | 17 | essential | 2020 | signposting | EV8-113 (HR 17) Makarska - Trpanj |  | 113 |  | 45 | SDŽ | 8500 | 1.3.5
5.1.6 | 18 | essential | 2020 | signposting | EV8-113 (HR 17) Makarska - Trpanj |  | 113 |  | 12 | DNŽ | 2000 | 1.3.5
5.1.6 | 19 | essential | 2020 | signposting | EV8-114 (HR 18) Trpanj - Ston |  | 114 |  | 54 | DNŽ | 7000 | 1.3.5
5.1.6 | 20 | essential | 2020 | signposting | EV8-115 (HR 19) Ston - Dubrovnik |  | 115 |  | 56 | DNŽ | 7000 | 1.3.5
5.1.7.1 | 1 | Essential | 2020 | local public transport | (Mošćenička Draga) Opatija-Rijeka | Ship |  |  |  | PGŽ | 2000 | 1.4.2
5.1.7.1 | 2 | Essential | 2020 | local public transport | Dubrovnik – Cavtat | Ship |  |  |  | DNŽ | 2000 | 1.4.2
5.1.7.1 | 3 | Essential | 2020 | local public transport | Mošćenička Draga (Opatija) – Rijeka | Bus |  |  |  | PGŽ | 2000 | 1.4.2
5.1.7.1 | 4 | Essential | 2020 | local public transport | Dubrovnik – Zvekovica (Cavtat) | Bus |  |  |  | DNŽ | 2000 | 1.4.2
5.1.7.1 | 5 | Important | 2020 | local public transport | Limski Kanal - Rovinj | Ship |  |  |  | IŽ | 2000 | 1.4.2
5.1.7.1 | 6 | Important | 2020 | local public transport | Rab – Lun | Ship |  |  |  | PGŽ | 1000 | 1.4.2
5.1.7.1 | 7 | Important | 2020 | local public transport | Rijeka – Križišće | Bus |  |  |  | PGŽ | 2000 | 1.4.2
5.1.7.1 | 8 | Important | 2020 | local public transport | Vodice - Šibenik | Bus |  |  |  | ŠKŽ | 2000 | 1.4.2
5.1.7.1 | 9 | Important | 2020 | local public transport | Šibenik – Grebaštica | Bus |  |  |  | ŠKŽ | 2000 | 1.4.2
5.1.7.1 | 10 | Important | 2020 | local public transport | Trogir – Kaštel Štafilić (Kaštel Stari) | Bus |  |  |  | SDŽ | 2000 | 1.4.2
5.1.7.1 | 11 | Important | 2020 | local public transport | Zaton – Dubrovnik | Bus |  |  |  | DNŽ | 2000 | 1.4.2
5.1.7.2 | 1 | Essential | 2020 | long distance public transport | Ljubljana – Pula, bike service | Train |  |  |  |  | 5000 | 1.4.2
5.1.7.2 | 2 | Essential | 2020 | long distance public transport | Rijeka – Pula | Bus |  |  |  |  | 4000 | 1.4.2
5.1.7.2 | 3 | Essential | 2020 | long distance public transport | Zagreb – Zadar – Šibenik – Split – Makarska – Ploče – Dubrovnik (two bus lines combined) | Bus |  |  |  |  | 8000 | 1.4.2
5.1.7.2 | 4 | Important | 2020 | long distance public transport | Rijeka – Zadar through Lika Rijeka – Zadar along the coast | Bus |  |  |  |  | 4000 | 1.4.2
5.1.7.2 | 5 | Essential | 2020 | long distance public transport | Catamaran line Pula – Mali Lošinj carrying bikes - reservation possible | Ship |  |  |  |  | 3000 | 1.4.2
5.1.7.2 | 6 | Important | 2025 | long distance public transport | Bike on Bus service Umag - Pula 2 per day | Bus |  |  |  |  | 4000 | 1.4.2
5.1.7.2 | 7 | Important | 2025 | long distance public transport | Bike on bus 2 per day to/from Maslenica, Nin, Biograd, Rogoznica, Primošten, Trogir, Omiš, Brela, Makarska, Drvenik, Ston, Slano, Trsteno, Cavtat | Bus |  |  |  |  | 8000 | 1.4.2
5.1.8 | 1 |  | 2025 | bike counters | Introduction of 2 bike counters |  |  |  |  | IŽ | 3000 | 1.7.1
5.1.8 | 2 |  | 2025 | bike counters | Introduction of 2 bike counters |  |  |  |  | PGŽ | 3000 | 1.7.1
5.1.8 | 3 |  | 2025 | bike counters | Introduction of 2 bike counters |  |  |  |  | LSŽ | 3000 | 1.7.1
5.1.8 | 4 |  | 2025 | bike counters | Introduction of 2 bike counters |  |  |  |  | ZŽ | 3000 | 1.7.1
5.1.8 | 5 |  | 2025 | bike counters | Introduction of 2 bike counters |  |  |  |  | ŠKŽ | 3000 | 1.7.1
5.1.8 | 6 |  | 2025 | bike counters | Introduction of 2 bike counters |  |  |  |  | SDŽ | 3000 | 1.7.1
5.1.8 | 7 |  | 2025 | bike counters | Introduction of 2 bike counters |  |  |  |  | DNŽ | 3000 | 1.7.1
5.2.1 | 1 |  | 2020 | bike rental | subvention of the bike rental network development - 4 stations | [5 empty] | 40000 | 2.3.3
5.2.1 | 2 |  | 2025 | bike rental | subvention of the e-bike rental development (e.g. 40% of 1500€, 250 bikes in total) | [5 empty] | 150000 | 2.3.3
5.2.1 | 3 |  | 2025 | bike rental | subvention of the bike rental network development - 10 stations | [5 empty] | 100000 | 2.3.3
5.2.2 | 1 | Essential | 2020 | bike service | service station on a daily section EV8-101 (HR 5) Rijeka - Bater | Bribir |  |  |  | PGŽ | 600 | 2.3.1
5.2.2 | 2 | Essential | 2020 | bike service | service station on a daily section EV8-105 (HR 9) Gospić - Lovinac | Lovinac |  |  |  | LSŽ | 600 | 2.3.1
5.2.2 | 3 | Essential | 2020 | bike service | service station on a daily section EV8-106 (HR 10) Lovinac - Maslenica | Maslenica |  |  |  | ZŽ | 600 | 2.3.1
5.2.2 | 4 | Essential | 2020 | bike service | service station on a daily section EV8-110 (HR 14) Šibenik - Trogir | Trogir |  |  |  | ŠKŽ | 600 | 2.3.1
5.2.2 | 5 | Essential | 2020 | bike service | service station on a daily section EV8-113 (HR 17) Makarska - Trpanj | Trpanj |  |  |  | DNŽ | 600 | 2.3.1
5.2.2 | 6 | Essential | 2020 | bike service | service station on a daily section EV8-114 (HR 18) Trpanj - Ston | Ston |  |  |  | DNŽ | 600 | 2.3.1
5.2.2 | 7 | Essential | 2020 | bike service | service station on a daily section EV8-116 (HR 20) Dubrovnik - granica | Cavtat |  |  |  | DNŽ | 600 | 2.3.1
5.2.2 | 8 | Important | 2020 | bike service | Subvention of the bike service marketing | [5 empty] | 3000 | 2.3.1
5.2.2 | 9 | Important | 2025 | bike service | Initiation of 10 new bike services | [5 empty] | 15000 | 2.3.1
5.2.3 | 1 | important | 2025 | bike taxi service | Subvention for bike racks for 2 small boats and water protection for 4 bikes for the line Novigrad (Istra) – Červar Porat | boat |  |  |  | IŽ | 1500 | 1.4.2
5.2.3 | 2 | important | 2025 | bike taxi service | Subvention for bike racks for 2 small boats and water protection for 4 bikes for the line Limski Kanal - Rovinj | boat |  |  |  | IŽ | 1500 | 1.4.2
5.2.3 | 3 | essential | 2020 | bike taxi service | Subvention for bike racks for 2 small boats and water protection for 4 bikes for the line Opatija - Rijeka | boat |  |  |  | PGŽ | 1500 | 1.4.2
5.2.3 | 4 | additional | 2030 | bike taxi service | Subvention for bike racks for 2 small boats and water protection for 4 bikes for the line Povljana – Vir | boat |  |  |  | ZŽ | 1500 | 1.4.2
5.2.3 | 5 | important | 2025 | bike taxi service | Subvention for bike racks for 2 small boats and water protection for 4 bikes for the line Srima – Šibenik | boat |  |  |  | ŠKŽ | 1500 | 1.4.2
5.2.3 | 6 | important | 2025 | bike taxi service | Subvention for bike racks for 2 small boats and water protection for 4 bikes for the line Trogir – Kaštel Štafilić | boat |  |  |  | SDŽ | 1500 | 1.4.2
5.2.3 | 7 | important | 2025 | bike taxi service | Subvention for bike racks for 2 small boats and water protection for 4 bikes for the line Kaštel Sućurac - Split | boat |  |  |  | SDŽ | 1500 | 1.4.2
5.2.3 | 8 | additional | 2030 | bike taxi service | Subvention for bike racks for 2 small boats and water protection for 4 bikes for the line Gradac - Ploče | boat |  |  |  | SDŽ/DNŽ | 1500 | 1.4.2
5.2.3 | 9 | important | 2025 | bike taxi service | Subvention for bike racks for 2 small boats and water protection for 4 bikes for the line Zaton - Dubrovnik | boat |  |  |  | DNŽ | 1500 | 1.4.2
5.2.3 | 10 | essential | 2020 | bike taxi service | Subvention for bike racks for 2 small boats and water protection for 4 bikes for the line Dubrovnik - Cavtat | boat |  |  |  | DNŽ | 1500 | 1.4.2
5.2.3 | 11 | additional | 2025 | bike taxi service | Subvention for bike racks for 4 taxi cars, 4 racks each | car |  |  |  | IŽ | 3000 | 1.4.2
5.2.3 | 12 | additional | 2025 | bike taxi service | Subvention for bike racks for 4 taxi cars, 4 racks each | car |  |  |  | PGŽ | 3000 | 1.4.2
5.2.3 | 13 | additional | 2025 | bike taxi service | Subvention for bike racks for 4 taxi cars, 4 racks each | car |  |  |  | LSŽ | 3000 | 1.4.2
5.2.3 | 14 | additional | 2025 | bike taxi service | Subvention for bike racks for 4 taxi cars, 4 racks each | car |  |  |  | ZŽ | 3000 | 1.4.2
5.2.3 | 15 | additional | 2025 | bike taxi service | Subvention for bike racks for 4 taxi cars, 4 racks each | car |  |  |  | ŠKŽ | 3000 | 1.4.2
5.2.3 | 16 | additional | 2025 | bike taxi service | Subvention for bike racks for 4 taxi cars, 4 racks each | car |  |  |  | SDŽ | 3000 | 1.4.2
5.2.3 | 17 | additional | 2025 | bike taxi service | Subvention for bike racks for 4 taxi cars, 4 racks each | car |  |  |  | DNŽ | 3000 | 1.4.2
5.2.6 | 1 | essential | 2020 | accomodation development | development of a simple bike-friendyl homestay with 5-6 beds |  |  |  |  | PGŽ | 15000 | 2.1.1
5.2.6 | 2 | important | 2020 | accomodation development | development of a simple bike-friendyl camping site for 10 tents |  |  |  |  | PGŽ | 10000 | 2.1.1
5.2.6 | 3 | essential | 2020 | accomodation development | development of two simple bike-friendyl homestay with 5-6 beds each |  |  |  |  | LSŽ | 30000 | 2.1.1
5.2.6 | 4 | additional | 2025 | accomodation development | development of simple bike-friendly food and accomodation capacity for 20 cyclists in Mogorić |  |  |  |  | LSŽ | 40000 | 2.1.1
5.2.7 | 1 | additional | 2025 | resting area | Bike resting area establishment between Križišće and Bribir |  |  |  |  | PGŽ | 8000 | 2.1.3
5.2.7 | 2 | additional | 2025 | resting area | Bike resting area establishment between Krivi put and Oltari |  |  |  |  | LSŽ | 8000 | 2.1.3
5.2.7 | 3 | additional | 2025 | resting area | Bike resting area establishment between Vrila Gacke and Perušić |  |  |  |  | LSŽ | 8000 | 2.1.3
5.2.7 | 4 | additional | 2025 | resting area | Bike resting area establishment between Gospić and Mogorić |  |  |  |  | LSŽ | 8000 | 2.1.3
5.2.7 | 5 | additional | 2025 | resting area | Bike resting area establishment in Mogorić |  |  |  |  | LSŽ | 8000 | 2.1.3
5.2.7 | 6 | additional | 2025 | resting area | Bike resting area establishment between Žuljana and Ston |  |  |  |  | DNŽ | 8000 | 2.1.3
5.2.8 | 1 |  | 2025 | bike & luggage storage | in total for 20 bikes on 2-3 locations |  |  |  |  | IŽ | 15000 | 2.3.2
5.2.8 | 2 |  | 2025 | bike & luggage storage | in total for 20 bikes on 2-3 locations |  |  |  |  | PGŽ | 15000 | 2.3.2
5.2.8 | 3 |  | 2025 | bike & luggage storage | in total for 20 bikes on 2-3 locations |  |  |  |  | LSŽ | 15000 | 2.3.2
5.2.8 | 4 |  | 2025 | bike & luggage storage | in total for 20 bikes on 2-3 locations |  |  |  |  | ZŽ | 15000 | 2.3.2
5.2.8 | 5 |  | 2025 | bike & luggage storage | in total for 20 bikes on 2-3 locations |  |  |  |  | ŠKŽ | 15000 | 2.3.2
5.2.8 | 6 |  | 2025 | bike & luggage storage | in total for 20 bikes on 2-3 locations |  |  |  |  | SDŽ | 15000 | 2.3.2
5.2.8 | 7 |  | 2025 | bike & luggage storage | in total for 20 bikes on 2-3 locations |  |  |  |  | DNŽ | 15000 | 2.3.2
5.3.1 | 1 | essential | 2020 | Internet | Web data maintenance in 2019. and 2020. | [5 empty] | 10000 | 3.3.2
5.3.1 | 2 | important | 2020 | Internet | Further web portal development (advanced features, social networks integration, newsletter, applictions) | [5 empty] | 8000 | 3.3.2
5.3.1 | 3 |  | 2020 | info center | EuroVelo 8 Croatia pilot hotline service | [5 empty] | 3000
5.3.1 | 4 | essential | 2025 | Internet | Web data maintenance in 2020. and 2021. | [5 empty] | 5000 | 3.3.2
5.3.1 | 5 | essential | 2025 | info system | Establishment of a self sustainable route information actualization system in 2021 | [5 empty] | 5000
5.3.3 | 1 | essential | 2020 | publishing | Organization of publishing printed map and guidebook for EuroVelo 8 route in Croatia | [5 empty] | 5000 | 3.3.3.
5.3.4 | 1 |  | 2020 | promotion | Diverse promotional actions in 2019 and 2020 total | [5 empty] | 40000 | 3.3
5.3.4 | 2 |  | 2025 | promotion | Diverse promotional actions 2021 - 2025 total | [5 empty] | 100000 | 3.3
5.3.5 | 1 |  | 2020 | marketing | Marketing plan until 2022. | [5 empty] | 10000 | 3.1.1
5.3.5 | 2 |  | 2025 | marketing | Marketing plan until 2030. | [5 empty] | 10000 | 3.1.1
5.3.5 | 3 |  | 2020 | marketing | Establishment of a system for cycling tourists information tracking (e.g. integration with e-visitor) | [5 empty] | 5000 | 3.1.2
5.3.5 | 4 |  | 2025 | marketing | Detailed route users surveys (counters, user feedback, questionnaires) and analysis | [5 empty] | 25000 | 3.1.2
5.4.1 | 1 |  | 2025 | organization | organization costs (manpower, travel costs, worshops etc.) 2021-2025.g. | [5 empty] | 150000 | 4.3.3
5.4.1 | 2 |  | 2030 | organization | organization costs (manpower, travel costs, worshops etc.) 2026-2030.g. | [5 empty] | 100000 | 4.3.3
5.4.2 | 1 |  | 2020 | route research | Route research and optimization up to 2020 | [5 empty] | 5000 | 4.2.1
5.4.2 | 2 |  | 2025 | route research | Route research and optimization 2021 - 2025 | [5 empty] | 15000 | 4.2.1
5.4.2 | 3 |  | 2030 | route research | Route research and optimization 2026 - 2030 | [5 empty] | 5000 | 4.2.1
5.4.4 | 1 |  | 2025 |  | certification of the part of the route | [5 empty] | 10000 | 4.4.2
5.4.4 | 2 |  | 2030 |  | certification of the complete route | [5 empty] | 10000 | 4.4.2
5.4.5 | 1 |  | 2020 |  | workshops and conferences in 2020 | [5 empty] | 5000 | 4.1.1
5.4.5 | 2 |  | 2025 |  | workshops and conferences 2021 - 2025 | [5 empty] | 20000 | 4.1.1
5.4.6 | 1 |  | 2020 |  | training and study tours until 2020 | [5 empty] | 18000 | 4.1.2
5.4.6 | 2 |  | 2025 |  | training and study tours 2021-2025 | [5 empty] | 18000 | 4.1.2